## Preparation Ext.Rev
| 2023 |  |  |  |  | 2024
Preparation of the Internal Review for the Award Renewal Phase | March | Sept. | Oct. | Nov. | Dec. | Jan | Febr | March | Abril | May | June
Internal Survey sent to identify the level of knowledge of HRS4R by the Research Community | bar: 2023 March
Review and update of HRS4R information in web and preparation of institutional video about HRS4R with the participation of research staff | bar: 2023 Sept.
Identifying needs for the new plan: A new survey had been planned to identify the needs for the new action plan, but given that meetings had been held with all research staff to prepare the new strategic plan, it was not considered necessary. The SWOT analysis carried out enabled the new strategic plan to be designed, which will guide the implementation of the new actions in the action plan. | bar: 2023 Oct.
Presentation of the status of the preparation of the Award Renewal Phase and the Action Plan to the Participation Groups: Steering Committee, Implementation WG and Working Groups to get new ideas for the new Action Plan. We will also update on this preparation phase in some meetings with research professionals in December. | bar: 2023 Nov.
Preparation and sending of the evaluation report for reaccreditation | bar: 2023 Dec.
Communication and awareness Campaign linked to surveys results adressed to all professionals | bar: 2024 Jan to 2024 March
Preparation of the site-visit with the collaboration of IWG and WG | bar: 2024 Jan
Simulation of site visit with researchers | bar: 2024 Febr
Site-Visit | 2024 Jan: Pending CE
Complete revision, preparation and publication of the NEW ACTION PLAN | bar: 2024 Jan to 2024 June

## PLAN EXTERNAL ASSESSMENT-revIWG
2019
Charter&Cod classification | Action number | C&C | Thematical Area (web) | RESPONSIBLE UNIT | TITLE ACTION | Description | INDICATORS / TARGET Detail of actions 2020 + until 2023 | Initial Timing for actions | FINAL DATE | Current Status (Completed/In progress/Pending/NEW) | Current Status// Remarks | Evidences
I. Ethical and Professional Aspects | A1 | ALL | 1. Ethical and professional aspects | General Direction, Communication Department and HR | Strength awareness, commitment and implementation of the Charter & Code criteria. | Strength awareness, commitment and implementation of the Charter & Code criteria. The goal of this action is to attain an increasing involvement of the C&C criteria in the research community and in everyday research practices. Specific planned actions: A.1.1 Prepare multilingual online material explaining the advantages of the application of the C&C principles and updates of the HRS4R web page, distribute it among all the researchers and incorporate this information into the Welcome Manual for newcomers. A.1.2 Schedule periodical briefings in departments to influence the dissemination of the C&C key lessons to research staff. . Schedule periodical briefings to the institution’s management committees and boards to introduce the OTM-R and C&C key lessons to the administration staff. . HR managers will attend workshops organised by European institutions to share good practices in the implementation of C&C actions. A.1.3 Incorporation of new researchers that wish to join the Implementation Working Group (IWG) for specific working teams and to become “Delegates for HRS4R”. A.1 4 Include the actions defined in this Action Plan in the new strategic plan of the FSJD. | A.1.1.The Charter&Code information has been made available on the HRS4R webpage, the intranet, the Welcome Manual, and the forms for registering new attached researchers. Additionally, the HR Department is communicating continuously actions related to HRS4R. In 2022 and 2023, we conducted two surveys to assess the level of awareness of HRS4R, which was found to be low. During the November 23 meeting with the IWG, we discovered that while people are aware of the improvements in the HR department but they do not always attribute them to the HRS4R seal. To address this, we will be conducting another awareness campaign and explaining the purpose of the seal again during annual meetings with researchers. Additionally, in 2023, we have improved the website to include all HRS4R-related documentation in a more structured manner. A1.2 Periodical meetings were held to explain what C&C is and provide updates onthe action plan. - Present the HRS4R in the annual meeting about "Plan de Gestión" presentation. - Discuss actions related to HRS4R in the weekly Institution Board meetings. - The HR Manager is registered in Euraxess to stay informed about events. - Meetings with other centers (IDIBAPS and ICFO) to learn about their best practices for implementing HRS4R. - Explain HRS4R in the annual meeting of Territorial Unit Boards. A.1.3 New members have been incorporated into the Working Groups. In September 2023, a new call for volunteers was made and 8 new delegates were identified. A.1.4 The Strategic Plan 2018-2022, including the HR-Action Plan's actions, has been updated. Also the new Strategic Plan 2024-2027 prioritises continuous improvement of HRS4R with a priority line: "Consolidate the People and Values model and optimise the IRSJD's scientific career model. The focus should be on attracting, retaining, stabilising and promoting talent to ensure the scientific sustainability of the organisation always having the HRS4R as a frame of reference" NEW A.1.5 Since 1 January 2020, the Ethics Committee, together with the Research Committee of our Research Institute, has agreed to establish a more efficient and secure project evaluation cycle. | Q1-Q3 2018 | Continuos | Completed | COMPLETED: We have finished the planned actions but maintaining the dissemination and awareness of C&C as an ongoing process of communication. | A.1.1. Web: https://www.irsjd.org/ca/recerca/hr-excellence-research-hrs4r/ Intranet:https://intranet.sanjuandedios.net/FDI/RRHHPers/RRHH/Paginas/HRS4RHRS4R.aspx Welcome Manual: \\hsjdbcn.es\dfsroot\Recursos\fsjd\fsjd_RRHH\Procedimiento de Acogida\Acogida individual New Video about HRS4R in SJD: https://youtu.be/VW8ECfNSSXE Forms for attached researchers.https://forms.office.com/pages/responsepage.aspx?id=Fmtb3aiPIEqBCwBpGZkzUORnsYugA7NCiuzPyZx2i9tUMUsxSlA4R0dQUkFJSklTUTVCNENZOTMxUi4u A.1.2 Welcome Group Meeting Presentations: https://pssjd-my.sharepoint.com/:p:/r/personal/vandres_hsjdbcn_es/Documents/ACOGIDA%20GRUPAL%202023.pptx?d=w5c761138c402408fb3f6b587849e6d6a&csf=1&web=1&e=YS4UTB Strategic Plan 2018-2022 and 2023-2027: \\hsjdbcn.es\dfsroot\Recursos\fsjd\fsjd_p\FSJD_DIRECCIO\PLA ESTRATEGIC Weekly Institution Board Intranet: https://intranet.sanjuandedios.net/FDI/OrganServ/CD/default.aspx Sant Antoni anual meeting presentation for Territorial Unit Boards: \\hsjdbcn.es\dfsroot\Recursos\fsjd\fsjd_RRHH\15. HRS4R Preparació i seguiment Action Plan Presentation of IWG Meeting november 23: \\hsjdbcn.es\dfsroot\Recursos\fsjd\fsjd_RRHH\15. HRS4R Preparació i seguiment Action Plan\PREPARACIÓN EXTERNAL EVALUATION\Revisió Action Plan novembre 23 Email as an example of dissemination of HRS4R. \\hsjdbcn.es\dfsroot\Recursos\fsjd\fsjd_RRHH\15. HRS4R Preparació i seguiment Action Plan\PREPARACIÓN EXTERNAL EVALUATION\Revisió Action Plan novembre 23\Evidencias\Acción 1 A.1.3 Members of WG: \\hsjdbcn.es\dfsroot\Recursos\fsjd\fsjd_RRHH\15. HRS4R Preparació i seguiment Action Plan\New Delegates Comissions de treball A.1.4 Objectives of the annual management plan related with Strategic Plan: \\hsjdbcn.es\dfsroot\Recursos\fsjd\fsjd_p\FSJD_DIRECCIO\CÚRIA\Plans de Gestió\2024\1. Pla de Gestió 24. New Strategic Plan 2024-2027: \\hsjdbcn.es\dfsroot\Recursos\fsjd\fsjd_p\FSJD_DIRECCIO\PLA ESTRATEGIC A.1.5 CEIM: https://www.sjdrecerca.org/es/servicios/servicios-de-gestion/comite-de-etica-de-la-investigacion-con-medicamentos-ceim/como-presentar-un-proyecto-al-ceim/
IV. Supervision: Training&Development | A2 | 11, 16, 17, 18, 19, 20, 21, 23, 25, 26, 28, 29, 30, 33, 37, 38, 39 | 3.Training and Development | General Direction and Scientific Direction + HR+ WG | Design and implement the FSJD’s Researchers’ Career Plan. | The Researchers’ Career Plan will define clear research career pathways, according to the same standards of the European R scale (https://euraxess.ec.europa.eu/europe/career-development/training-researchers/research-profiles-descriptors), and should include information on: revised salary scales, career stabilisation plan, and the functions and responsibilities derived from the positions. Also, it will emphasise the positive value of intersectoral or transdisciplinary mobility, and the participation in research networks. Additionally, it will clearly describe the minimum qualifications needed to enable the promotion to a higher research step. The institution has its own stabilisation policy for “Miguel de Servet” and “Ramon y Cajal” researchers, if they meet the recruiting criteria, and funding is provided. For the remaining researchers, mentoring in professional pathways or alternatives to research will be provided. For young researchers: Give support to train and develop the next generation of research leaders, support excellent individuals at critical points of their careers and help address research skills priorities identified with partners. | A2.1 Researchers’ Career Plan defined, published on line and multilingual: Document elaborated and approved by the Working Group. Every year we have a meeting with the Working Group in order to identify improvements for the document. For example, in 2023 we identified a new stage in career call R2AR for long term post-doctoral researchers. A2.2 Researchers’ Career Plan available online and in the Welcome Manual A2.3 Guide for training junior scientists published online and multilingual: In the 2020 training plan, we introduced trainning in Soft Skills to improve professional competences defined in the Career Plan document. In 2023, we have develop a Specific Leadership Programme (36h) for Management and Research junior leaders. A2.4 Researchers classified internally according to R Scale. | Q2-Q3 2018 | March 2020 | Completed | COMPLETED Researchers’ Career Plan is defined but for next years is important to implement and follow the model for all the Researchers. Yearly revision with Working Group | A2.1 https://www.irsjd.org/media/upload/domain_3/arxius/HRS4R/2023/ANG-IRSJD-categories_professionals.pdf Records of meetings and presentations shared with WG saved in FSJD Directory and document published https://www.irsjd.org/media/upload/domain_3/arxius/HRS4R/2023/CAT-IRSJD-categories_professionals.pdf Corporate communications: \\hsjdbcn.es\dfsroot\Recursos\fsjd\fsjd_RRHH\15. HRS4R Preparació i seguiment Action Plan\PREPARACIÓN EXTERNAL EVALUATION\Revisió Action Plan novembre 23\Evidencias\Acción 2 A2.2 https://intranet.sanjuandedios.net/FDI/DocuMulti/Docu/Biblioteca_documentos/Departament%20Persones%20(RRHH)/2023%20Welcome%20Handbook.pdf A2.3 https://www.irsjd.org/media/upload/domain_3/arxius/formacio/recommended-actions_210122.pdf
IV. Supervision: Training&Development | A3 | 11, 16, 17, 18, 19, 20, 23, 28, 29, 33, 36 | 3.Training and Development | General Direction and Scientific Direction + HR+ WG | Design and implement the FSJD’s Career Evaluation Process. | This process will be aligned with the Research Career Plan and should clearly establish and measure the impact of positive criteria for the performance evaluation, such as: performance of training courses, mobility, direction of Ph.D. theses, mentorship or junior scientist training, etc. | A3.1 Career Evaluation Process protocols defined in the same document of Researcher's Career Plan. A3.2 Written a paragrah about evaluation commitees this point in Career Evaluation Process A3.3 Career Evaluation Process available online and in the Welcome Manual. A4.4 At the end of 2023, we have designed a new Programme called VALORa as a development assessment process. | Q4 2018-Q1 2019 | March 2020 | Completed | COMPLETED Career Evaluation Process protocols are defined but for the next years is important to implement the model. Yearly revision with Working Group | A3.1/ A3.2/ A3.3 https://www.irsjd.org/media/upload/domain_3/arxius/HRS4R/2023/ANG-IRSJD-categories_professionals.pdf Records of meetings and presentations shared with WG saved in FSJD Directory and document published https://www.irsjd.org/media/upload/domain_3/arxius/HRS4R/2023/CAT-IRSJD-categories_professionals.pdf Corporate communications: \\hsjdbcn.es\dfsroot\Recursos\fsjd\fsjd_RRHH\15. HRS4R Preparació i seguiment Action Plan\PREPARACIÓN EXTERNAL EVALUATION\Revisió Action Plan novembre 23\Evidencias\Acción 3 A3.4 VALORa Program https://intranet.sanjuandedios.net/FDI/DocuMulti/Docu/Biblioteca_documentos/Forms/AllItems.aspx?RootFolder=%2FFDI%2FDocuMulti%2FDocu%2FBiblioteca%5Fdocumentos%2FDepartament%20Persones%20%28RRHH%29%2FCarreres%20i%20valoraci%C3%B3%20del%20rendiment%20per%20personal%20investigador
III. Recruitment | A4 | 12, 13, 14, 15 | 2. Recruitment and Welcome | Scientific Direction + HR and WG | Design and implement the FSJD’s Recruitment Procedure, based upon OTM-R criteria. | A.4.1 Creation of the “OTM-R Implementation working team” with the task of reviewing the processes of selection and recruitment of researchers for the progressive adaptation to the OTM-R system A 4.2 Development of a protocol and a guide for implementation of the OTM-R system in the recruitment of researchers. A recruitment committee will be set up ad hoc to oversee the evaluation of the candidates. A 4.3 Training actions for researchers on implementation of the OTM-R system A 4.4. For hiring researchers through R&D&I Project Funding: Providing clear procedures and scoring scales for the qualification required for each call. The calls will be published in Euraxess and other online platforms. A 4.5 A recruitment Comittee will be set up ad hoc to oversee the evaluation of candidates. A 4.6 The FSJD’s multilingual web portal on job opportunities (TRABAJA CON NOSOTROS) will include both job offers and a repository of information on selection and recruitment procedures. A 4.7 A written guideline for Recruitment Procedure will be available. A 4.8 If necessary, specific training will be provided to the technicians and researchers involved in recruiting processes. | A4.1 OTM-R working team selected in july 2019. A4.2 OTM-R protocol and guide defined and published online. A4.3 The web portal of job opportunities has been developed to an online system for the reception of candidates (Talent Clue) A.4.4 Recruitment Procedure Available (published 10th february 2020) and centralized in HR Department. A 4.5 Recruitment training sessions organized in 2022 and in 2023. A 4.6 Meeting with PIs in march 2023 to improve the recruitment process and give more support from HR Department (related with labour reform A 4.7 Recruitment KPIs shared with Working Group to improve. A 4.8 New tools: Forms for new Hirings to identified Recruitment Process Code// Forms for new job offers to identifie who will be member of the Recruitment Comitee/ Forms for evaluation of candidates. | Q2 2019 | Continuos | Completed | COMPLETED The Recruitment Procedure was published in february 2020. We have done several reviews of the process as we have a yearly revision with Working Group. We have some tools to monitorize the process and KPIs for the following of activities. As a weak point, the forms for evaluation is not enough used. Also we have to continue raising awareness the importance of Recruitment Comitees. We have give the tools but this two last points should be improved. | A.4.1 Working Team: https://www.irsjd.org/en/research/hr-excellence-research-hrs4r/staff-selection-and-welcome/ A.4.2 OTM-R Protocol: https://www.irsjd.org/media/upload/domain_3/arxius/formacio/hrs4r/2020-OTM_R-Checklist-FSJD.pdf A.4.3 Talent Clue: https://www.irsjd.org/en/research/working-at-the-irsjd/ A.4.4 Procedure: https://www.irsjd.org/media/upload/domain_3/arxius/HRS4R/2023/FSJD-Principios-procedimientos-seleccion-2023-ang.pdf A.4.5 Training Sessions: Getting the Right Person for your Team in 2022 https://formacion.sjdhospitalbarcelona.org/pub/media/pdftoproduct/k/n/knowledge_path_2022_1.pdf Recruitment (in Leadership Program 2023) A.4.6 Corporate presentations: https://intranet.sanjuandedios.net/FDI/DocuMulti/Docu/Biblioteca_documentos/Departament Persones (RRHH)/PRINCIPIOS Y PROCEDIMIENTO SELECCI%C3%93N 2022 CAST.pdf A.4.7 KPIs: \\hsjdbcn.es\dfsroot\Recursos\fsjd\fsjd_RRHH\21.INDICADORES\2023 A 4.8 New tools: https://forms.office.com/e/vci8PthGv5
IV. Supervision: Training&Development | A5 | 2,5,31,33,37,38,39 | 3.Training and Development | Scientific Direction+ HR+ WG | Design and implement the FSJD’s Training Plan for researchers. | Profiling the professional qualifications and skills for each of the categories of the R scale in the Researchers’ Career Plan. The profiling will be used as a tool for identifying training needs for each category. Perform a survey to identify the training needs. Include in the survey topics like: IP in biomedicine, technology transfer, data protection, ethics in research, prevention of labour risks, data protection policy, languages (English), and soft or transversal skills. Additionally, specific training about clinical studies will be provided to those researchers implicated. Define a training plan and organise these courses. Update the online documents repository. Perform a concise evaluation of the merits of the researchers in charge of the training of new researchers, and revise the teaching load of the researcher before the assignation of a junior scientist for training. | A5.1 Survey performed and analysed: In March 2019, we had identified training needs with IRSJD Scientific Manager and Research Unit Direction PSSJD. Identified needs about: technology transfer, data protection, ethics in research, prevention of labour risks, data protection policy, clinical studies and soft skills. In October 2019, was created the Working Group for 2020 and a survey was sent to identify needs. A5.2 Training Plan defined for 2019-2023: Knowledge Path A5.3 Training Plan available online and in the Welcome Manual. A5.4 Evaluation of the teaching load before assigning new training responsibilities: For every course there's a survey to evaluate satisfaction with the course. A5.5 Yearly KPIs to analyse trainning plan A5.6 In 2023, we review the training plan to adapt it to the European Framework. | Q3 2019 | Continuos | Completed | COMPLETED : Yearly Plan | A5.1 Surveys and meetings with Working Group: \\hsjdbcn.es\dfsroot\Recursos\fsjd\fsjd_RRHH\3. FORMACIÓN A5.2/ A5.3 View yearly plan in: https://formacion.sjdhospitalbarcelona.org/es/especialidades/investigacion.html https://www.irsjd.org/ca/recerca/hr-excellence-research-hrs4r/formacio-i-desenvolupament-pla-de-formacio/ A5.4 Annual analysis of satisfaction with each training course \\hsjdbcn.es\dfsroot\Recursos\fsjd\fsjd_RRHH\3. FORMACIÓN\2022\Tancament Programa A5.5 Follow-up KPIs: \\hsjdbcn.es\dfsroot\Recursos\fsjd\fsjd_RRHH\21.INDICADORES\2023
| A6 | 4, 32, 33, 34, 35 | 1. Ethical and professional aspects | Scientific Direction | Update the FSJD’s Research Committee attributions. | Redefine its activities, composition, assignment times and operating mechanisms. Include in its composition the members of all the scientific scales of researchers. In cases of complaints or disputes, the research committee will act as an ombudsman examining and judging the situation. It will be assured that no conflicts of interest will rise between the members of the Research Committee in the judgement of a situation. It will also mediate and solve co-authorship related conflicts, and good scientific practices issues. Additionally, it will revise the Ph.D. co-direction guidelines. Write a Guide for the new Research Committee attributions, published online and multilingual. | A.6.1 Research Committee reformed with new responsibilities. A.6.2 Research committee Guide defined and published online and multilingual. | Q4 2019 | Q4 2019 | Completed | COMPLETED | A.6.1/ A.6.2 Web: https://www.irsjd.org/en/research/hr-excellence-research-hrs4r/ethical-and-professional-aspects/ https://www.irsjd.org/en/institute/research-committee/
| A7 | 5,8,31 | 1. Ethical and professional aspects | Innovation Direction | Define the FSJD’s Tech Transfer Policy. | A Tech Transfer Policy will be defined accordingly with present procedures. A specific clause of current IP regulations of the Institution will be included in the new contracts and info will be distributed to the newcomers, for their signed ratification. Will also be multilingual versions. Training courses on Tech Transfer and IP will be provided. | A.7.1 Tech Transfer plan defined and published. A.7.2 IP regulation clause included in all new contracts. A.7.3 Training courses on IP available online and in-person. | Q1 2020 | Continuos | Completed | COMPLETED | A.7.1 Web: https://www.irsjd.org/en/innovation/tech-transfer-policy/ https://intranet.sjdhospitalbarcelona.org/sites/serveis/serveissuport/SitePages/Pol%C3%ADtica-de-Propietat-Intelectual-i-Industrial.aspx?web=1 A.7.2 Contract example: \\hsjdbcn.es\dfsroot\Recursos\fsjd\fsjd_RRHH\15. HRS4R Preparació i seguiment Action Plan\PREPARACIÓN EXTERNAL EVALUATION\Revisió Action Plan novembre 23\Evidencias\Acción 7 A.7.2 Training: https://tecsam.org/activities/training/ https://www.innovation4kids.org/en/training-capsules/ https://xartecsalut.com/
IV. Supervision: Training&Development | A8 | 33, 36,37, 38, 39, 40 | 3.Training and Development | Scientific Direction +IWG | Improving PhD and Post Doc supervision. | Emphasise the academic supervision of junior researchers as a first step in the development of their research career, establishing clearly their rights and duties of each scientific position, providing feedback of their performance, and insisting on the internationalisation of their careers by mobility actions or the participation in scientific networks. For R3 and R4 researchers in charge of the supervision, benchmark of international practices on functions and skills for the supervision of PhD and postdoctoral researchers (analysis of responsibilities, processes and monitoring mechanisms, etc.) Preparation of a guide of good practices of academic supervision and direction of thesis published online and multilingual. Pilot project for the development of the position of Supervisor of Post Docs. | A.8.1 Guide of good practices of supervision and direction of theses published online and multilingual. Ok A8.2 Ph.D. and Post Doc supervision benchmark report pending A8.3 Pilot Project of supervision of Post Docs finished. In Mentoring Program is included a point about Post-Doc supervision but with the new IRSJD management this will be a point to work. | Q3 2020 | Pending | In progress | IN PROGRESS | A.8.1 https://www.irsjd.org/en/research/hr-excellence-research-hrs4r/training-and-development-professional-categories-career-and-evaluation/
IV. Supervision: Training&Development | A9 | 11, 16, 17, 18, 19, 20, 23, 28, 29, 30, 33, 36, 40 | 3.Training and Development | Scientific Direction +IWG | Design and implement the FSJD’s Mentorship Programme | Conduct a satisfaction survey for various stakeholders on doctoral education (students, supervisors, coordinators, etc.) Benchmark of international practices on functions and skills for mentorship. The Mentor, as a more experienced and senior person, should guide and advise junior researchers about the most appropriate way to develop his /her talent for answering personal and professional challenges of his life, and to seek, if necessary, alternative opportunities inside or outside the research career. Design the FSJD’s Mentorship Programme, including both career development advice (mobility, training, professional paths, etc.), and academic advice. Preparation of a guide of good mentorship practices published online and multilingual. Set up a pilot mentorship programme. Training courses for Mentors will be mandatory. | A9.1 Mentorship Programme defined and published. A9.2 Guide of mentorship programme defined and published online and multilingual. A9.3 Pilot on mentorship performed. A9.4 Training courses on mentorship available. | Q4 2020 | 2023 | Completed | COMPLETED: We have launched a pilot that will be reviewed | A9.1/2/3 Mentoring Program: https://www.irsjd.org/media/upload/domain_3/arxius/HRS4R/2023/ CAT-Programa-Pilot-Mentoria_v4-FINAL.pdf A9.1/2/4 Training Courses on Mentoring done in 2023: \\hsjdbcn.es\dfsroot\Recursos\fsjd\fsjd_RRHH\2. DESARROLLO PROFESIONAL\MENTORING\Sesiones formativas
| A10 | 9 | 1. Ethical and professional aspects | Communication Department | Design the FSJD’s Outreach Plan. | Improvement of the present outreach activity by defining, preparing and implementing an “Outreach plan” to coordinate and improve all the outreach activities of the institution. Assign the outreach competencies to the Communication Department, specifically to one staff member. Identify and support potential science disseminators willing to perform outreach activities. Training courses on outreach will be provided. | A10.1 FSJD Outreach Plan defined. A10.2 Outreach leader assigned. A10.3List of the most active science disseminators researchers created. A10.4 Training courses on outreach available. | Q22020 | Continuos | Completed | COMPLETED: We have finished the planned actions but maintaining OutReach activities as an ongoing process of communication. | https://www.irsjd.org/en/collaborate/
III. Working Conditions and Social Security | A11 | 27 | 4.Working Conditions | HR Department and WG | Design and implement the FSJD’s Gender Plan. | Study the present scope of gender issues at FSJD. Define, prepare and implement the FSJD’s Gender Plan. Include these competencies in the RH department, specifically assigning them to one staff member. Create guidelines for gender published online and multilingual. Training courses on gender will be provided. | A11.1 Gender diagnosis at FSJD done. A11.2Gender plan performed. A11.3 Gender plan leader assigned. A11.4 Guidelines for gender equality defined and published online and multilingual. A11.5 Training courses on gender available online. A11.6 Action plan and KPIS of the gender plan followed by the Working Group. A11.7 Sexual Harassment Protocol reviewed and published. A11.8 Activities done to give visibility to Women in Science | Q12021 | December 2020 | Completed | COMPLETED | A11.1/2/3/4/6 Web: https://www.irsjd.org/ca/recerca/hr-excellence-research-hrs4r/condicions-seguretat-igualtat-de-genere/ Training: Preventor platform and training courses in training plan 2021.
I. Ethical & Professional Aspects | A12 | 2, 3, 4, 7, 8, 31, 36 | 2. Recruitment and Welcome | HR Department | Write the FSJD’s Welcome Manual. | The manual will include all the information concerning the procedures, rules, policies and resources available for the correct development of the research career at the Institution, such as: research ethics, good laboratory practices, notebook completion and storage actions, risk protection, data protection policies, IP regulation, tech transfer, gender policy, flexible working hours, complaints procedures, relation with supervisors and mentors, etc. The information provided will be updated periodically, so that Evolutionary versions will be elaborated. The Welcome Manual will be available online and multilingual to all newcomers and present research staff. | A12.1 FSJD Welcome Manual versions published online and multilingual: April 2019: Welcome programme and manual updated and documents including information about HRS4R. A12.2 Also we are also holding quarterly group welcome sessions where we explain procedures and present HRS4R. | Q2 2021 | View detail below | Completed | COMPLETED: Continuos revisions as the information could be updated | A12.1 Welcome Manual: https://intranet.sanjuandedios.net/FDI/DocuMulti/Docu/Biblioteca_documentos/Departament%20Persones%20(RRHH)/2023%20Welcome%20Handbook.pdf A12.2 Welcome Group Sessions https://intranet.sanjuandedios.net/FDI/DocuMulti/Docu/Biblioteca_documentos/Departament%20Persones%20(RRHH)/ACOGIDA%20GRUPAL%202023-JULIOL%20DEF.pdf
I. Ethical & Professional Aspects | A13 | 2, 23, 24, 36, 37, 40 | 1. Ethical and professional aspects | Scientific Direction | Update the FSJD’s Code of Good Practices in Research. | Update the code of Good Practices in including actions, recommendations and commitments for the development of research activities. The update will cover topics like: data protection, IP rights, personal and professional life balance, etc. The Code of Good Practices will be available online and multilingual to all newcomers and present research staff. Additionally, FSJD is presently performing a revision of the ethical committee evaluation process to diminish the project submission and approval time, contributing directly to the improvement of good practices in research at the institution. At the Action Plan we had identifiy this action: Centralise the management of Laboratory notebooks for all the Institution and name a person in charge. However, due to the growth of the Institution, it has not been considered possible to carry out this action at an operational level. | A13.1 FSJD Code of Good Practices in Research updated published online and multilingual. • Laboratory notebooks leader assigned. A13.2 An Ombudsperson it's being nominated | Q3 2021 | Q3 2021 | Completed | COMPLETED | A13.1 Code of Best Scientific Practices: https://www.irsjd.org/media/upload/domain_3/arxius/recerca/ANG-IRSJD-code-of-best-scientific-practices-2023.pdf A13.2 Ombudsperson: https://www.irsjd.org/en/institute/ombudsperson/
III. Working Conditions and Social Security | A14 | 7 | 4.Working Conditions | HR Department and PRL Dpt. | Implementation of occupational risk prevention measures. | Revise the status of the ergonomics condition at the FSJD’s workplaces. Performing actions to improve safety and health conditions in workplaces, facilities, equipment and processes. Implementation of occupational risk prevention measures assessed as significant in the risk assessment plan. | A14.1 Report of the status of the ergonomic conditions done. A14.2 Occupational risk prevention plan revisited. A14.3 Safelab: quarterly. A14.4 Mai 2019: Biosecurity Evaluation (external company) A14.5 April 2019: Review of PRL documents delivered in Welcome and Intranet A14.6 April 2019 and 2022: Results of the psychosocial risk stud (ARPS) and action plan A14.7 Biosecurity responsible identified and Biosecurity Manual sended to all employees in 2022 | Q4 2021 | Q4 2021 | Completed | COMPLETED Yearly Plan | A14 All the documents in: \\hsjdbcn.es\dfsroot\Recursos\prlhsjdfsjd Web: https://www.irsjd.org/en/research/hr-excellence-research-hrs4r/conditions-safety-safelab/ Biosecurity actions: \\hsjdbcn.es\dfsroot\Recursos\fsjd\fsjd_RRHH\15. HRS4R Preparació i seguiment Action Plan\PREPARACIÓN EXTERNAL EVALUATION\Revisió Action Plan novembre 23\Evidencias\Acción 14
| A15 | 8 | 1. Ethical and professional aspects | Knowledge Management Unit | Update the Open Science policy and development/dissemination/teaching of new tools for researchers | With the hiring in 2023, of a person responsible for Open science and Data Management we are developing an action plan in this area: Update the Open Access policy to a full fledged Open Science policy. Update and/or develop new protocols for the management of open publications and FAIR research data Develop an institutional Data Management Plan templantes&guidelines as well as the institutional instance in einaDMP service by CSUC Creation of an institutional FAIR research data repository Continue offering training courses about Open Science | A15.1 Open Science policy approved and disseminated to the research community A15.2 Institutional Data Management Plan template&guidelines for Horizon Europe and Agencia Estatal de Evaluación, at least, developed. A15.3 Instance in einaDMP fully setup and operational, with data management plan templates and guidelines implemented, and disseminated to researchers. A15.4 Data Management plan elaboration support service launched. A15.5 Instance in CORA RDR FAIR research data fully setup and operational, agreement with CSUC signed, dissemination and deposit suport institutional service running. A15.6 At least 2 Open Science training sessions done each year. | 2024 | 2024 | NEW | In 2023 Q3-Q4 advancedments have been done regarding: -Institutional Data Management Plan template & guidelines first draft has been done -EinaDMP instance creation and initial setup done, not yet lanched/disseminated -Agreement with CSUC to use CORA RDR FAIR research data revised, not yet signed. The institutional instance is created but not fully setup
| A.16 | ALL | 1. Ethical and professional aspects | General Direction, Communication and HR | Strength awareness, commitment and implementation of NEW Charter & Code criteria. | It is essential to maintain the commitment and implementation of the Charter & Code, adapting the actions to the new Charter and Code for Researchers, taking into account Open Science, Integrity, Gender... | A16.1 Documents related to new principles elaborated and published (gender, open science, integrity, ...) A16.2 Action Plan updated incorporating any new principles that could be established | 2024-2025 | 2024-2027 | NEW
| A17 | 11,12, 13, 14, 15 | 2. Recruitment and Welcome | Scientific Direction + HR and WG | Improve Researchers Assessment system in Recruitment | A.18 In the recruitment process, we need to improve the researcher evaluation system, which takes into account the new European Competence Framework for Researchers, called ResearchComp. | A17.1 A new system for new hirings for Researchers Assessment published A17.2 Number of Assessments done for Researchers Career Positions | 2025 | 2025 | NEW
| A18 | 27 | 4.Working Conditions | HR Department and WG | Design and implement the FSJD’s New Gender Plan. | Study the present scope of gender issues at FSJD. Define, prepare and implement the FSJD’s Gender Plan. Include these competencies in the RH department, specifically assigning them to one staff member. Create guidelines for gender published online and multilingual. Training courses on gender will be provided. | A18.1 Gender diagnosis at FSJD done. A18.2 Gender plan performed. A18.3 Gender plan leader assigned. A18.4 Guidelines for gender equality defined and published online and multilingual. A18.5 Training courses on gender available online. A18.6 Action plan and KPIS of the gender plan followed by the Working Group. A18.7 Outreach Activities done | 2024 | 2024-2029 | NEW
| A19 | 23 | 4.Working Conditions | Infraestructure Manager and HR Department | Plan of Infraestructures and Sustanaibility of Research | New incorporation of Infrastructure Manager and deployment of an action plan. This action plan will promote the sustainable implementation of research activities in line with the European Green Deal. We have to develop a plan to reduce our carbon emissions. | A19.1 Infraestructure Policies defined and implemented A19.2 Plan for reducing carbon emissions elaborated | 2025 | 2024 | NEW
| A20 | 11, 16, 17, 18, 19, 20, 21, 25, 26, 28, 29, 30, 33, 37, 38, 39 | 3.Training and Development | Scientific Direction+ HR+ WG | Review and implement new talent policies | Aligned with the new Governances and Strategy Plan, and taking into account the talent fund, review and implement new talent policies adressed to: - Improve and optimise the IRSJD scientific career model - Attract talent creating specific Calls for different profiles. - Define and implement new strategies to retain and develop internal talent: the stabilisation policy for "Miguel de Servet" and "Ramon y Cajal" researchers needs to be reviewed. | A20.1 Career Evaluation Criteria and Process reviewed A20.2 New Calls for specific profiles opened A20.3 Stabilisation policy reviewed and published | 2024 | 2024-2026 | NEW

## Cronogram Reviewed Dec.23
Nº | TITLE ACTION - INDICATORS / TARGET | STATUS IN DECEMBER 2023 | 2018 |  | 2019 |  |  |  | 2020 |  |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | According to initial planning
|  |  | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Delayed
A1 | Strength awareness, commitment and implementation of the Charter & Code criteria. | COMPLETED (continuos improvement) | [38 empty] | Done | bar: 2018 Q3 to 2019 Q4
| Online documents, available on: HRS4R web page and Welcome Manual. | Ok | [38 empty] | Pending | bar: 2019 Q1 to 2019 Q2
| Periodical briefings celebrated. | Ok
| New members at the Implementation Working Group. | Ok | bar: 2019 Q2
| Strategic Plan including HR-Action Plan’s actions. | Ok | bar: 2018 Q3
A2 | Design and implement the FSJD’s Researchers’ Career Plan. | COMPLETED (continuos improvement) | bar: 2018 Q3 to 2018 Q4; 2019 Q3 to 2020 Q1
| Researchers’ Career Plan defined and published on line and multilingual. | Ok | bar: 2019 Q1; 2020 Q1
| Researchers’ Career Plan available online and in the Welcome Manual. | Ok | bar: 2019 Q1; 2020 Q1
| Guide for training junior scientists published online and multilingual. | Ok | bar: 2019 Q1; 2020 Q1
A3 | Design and implement the FSJD’s Career Evaluation Process. | COMPLETED (continuos improvement) | bar: 2018 Q4 to 2019 Q1; 2019 Q4 to 2020 Q1
| Career Evaluation Process protocols defined. | Ok | bar: 2018 Q4; 2020 Q1
| Guidelines to the selection of independent evaluation committees written on line and multilingual. | Ok | bar: 2018 Q4; 2020 Q1
| Career Evaluation Process available online and in the Welcome Manual. | Ok | bar: 2019 Q1; 2020 Q1
A4 | Design and implement the FSJD’s Recruitment Procedure, based upon OTM-R criteria. | COMPLETED (continuos improvement) | bar: 2019 Q2 to 2020 Q1
| OTM-R working team selected. | Ok | bar: 2019 Q2 to 2019 Q3
| OTM-R protocol defined and published online. | Ok | bar: 2019 Q2; 2020 Q1
| OTM-R Guide defined and published online and multilingual. | Ok | bar: 2019 Q2; 2020 Q1
| Guideline for Recruitment Procedure defined and published online and multilingual. | Ok | bar: 2019 Q2; 2020 Q1
| Recruitment Procedure available online and in the Welcome Manual. | Ok | bar: 2019 Q2; 2020 Q1
A5 | Design and implement the FSJD’s Training Plan for researchers. | COMPLETED (continuos improvement) | bar: 2019 Q2 to 2019 Q3; 2020 Q1
| Survey performed and analysed. | Ok | bar: 2019 Q3; 2020 Q1
| Training Plan defined. | Ok | bar: 2019 Q3; 2020 Q1
| Training Plan available online and in the Welcome Manual. | Ok | bar: 2019 Q3; 2020 Q1
| Evaluation of the teaching load before assigning new training responsibilities | Ok | bar: 2019 Q4
A6 | Update the FSJD’s Research Committee attributions. | COMPLETED (continuos improvement) | bar: 2019 Q4
| Research Committee reformed with new responsibilities. | Ok | bar: 2019 Q4
| Research committee Guide defined and published online and multilingual. | Ok | bar: 2019 Q4
A7 | Define the FSJD’s Tech Transfer Policy. | COMPLETED (continuos improvement) | bar: 2019 Q4
| Tech Transfer plan defined and published. | Ok | bar: 2019 Q4
| IP regulation clause included in all new contracts. | Ok | bar: 2019 Q4
| Training courses on IP available online and in-person. | Ok | bar: 2019 Q4
A8 | Improving PhD and Post Doc supervision. | IN PROGRESS | bar: 2023 Q4
| Ph.D. and Post Doc supervision benchmark report performed. | Pending | bar: 2023 Q4; 2025 Q1
| Guide of good practices of supervision and direction of thesis published online and multilingual. | Ok | bar: 2023 Q4
| Pilot Project of supervision of Post Docs finished. | Pending | bar: 2023 Q4; 2025 Q3
A9 | Design and implement the FSJD’s Mentorship Programme | COMPLETED (continuos improvement) | bar: 2020 Q4 to 2021 Q2; 2023 Q3
| Benchmark of international Mentorship Programmes done. | Ok | bar: 2020 Q4; 2023 Q3
| Mentorship Programme defined and published. | Ok | bar: 2021 Q1; 2023 Q3
| Guide of mentorship programme defined and published online, multilingual. | Ok | bar: 2021 Q1; 2023 Q3
| Pilot on mentorship performed. | Ok | bar: 2021 Q2; 2023 Q3
| Training courses on mentorship available. | Ok | bar: 2021 Q2; 2023 Q3
A10 | Design the FSJD’s Outreach Plan. | COMPLETED (continuos improvement) | bar: 2020 Q1
| FSJD Outreach Plan defined. | Ok | bar: 2020 Q1
| Outreach leader assigned. | Ok | bar: 2020 Q1
| List of the most active science disseminators researchers created. | Ok | bar: 2020 Q1
| Training courses on outreach available. | Ok | bar: 2020 Q1
A11 | Design and implement the FSJD’s Gender Plan. | COMPLETED (continuos improvement) | bar: 2019 Q4 to 2020 Q4
| Gender diagnosis at FSJD done. | Ok | bar: 2020 Q2 to 2020 Q3
| Gender plan preformed. | Ok | bar: 2020 Q4
| Gender plan leader assigned. | Ok | bar: 2020 Q2
| Guidelines for gender equality defined and published online, multilingual. | Ok | bar: 2020 Q4
| Training courses on gender available online. | Ok | bar: 2021 Q1
A12 | Write the FSJD’s Welcome Manual. | COMPLETED (continuos improvement) | bar: 2019 Q1 to 2020 Q2
| FSJD Welcome Manual versions published online and multilingual. | Ok | bar: 2018 Q3; 2019 Q2; 2020 Q1
A13 | Update the FSJD’s Code of Good Practices in Research. | COMPLETED (continuos improvement)
| FSJD Code of Good Practices in Research updated published online and multilingual. | Ok
| Laboratory notebooks leader assigned. | Cancelled
A14 | Implementation of occupational risk prevention measures. | COMPLETED (continuos improvement) | bar: 2019 Q1 to 2020 Q3
| Report of the status of the ergonomic conditions done. | Ok | bar: 2019 Q2
| Occupational risk prevention plan revisited. | Ok | bar: 2019 Q3
| To prepare the internal and external review | Ok | bar: 2018 Q3 to 2023 Q4
A15 | Update the Open Science policy and development/dissemination/teaching of new tools for researchers | NEW- 2024
| Open Science policy approved and disseminated to the research community | Q4 2024 | bar: 2024 Q4
| Institutional Data Management Plan template&guidelines for Horizon Europe and Agencia Estatal de Evaluación, at least, developed. | Q4 2024 | bar: 2024 Q4
| Instance in einaDMP fully setup and operational, with data management plan templates and guidelines implemented, and disseminated to researchers. | Q3 2024 | bar: 2024 Q3
| Data Management plan elaboration support service launched. | Q3 2024 | bar: 2024 Q3
| Instance in CORA RDR FAIR research data fully setup and operational, agreement with CSUC signed, dissemination and deposit suport institutional service running. | Q3 2024 | bar: 2024 Q3
| At least 2 Open Science training sessions done each year. | Q4 2024 | bar: 2024 Q4; 2025 Q4; 2026 Q4; 2027 Q4
A16 | Adapt the actions to the new Charter and Code for Researchers, taking into account Open Science, Integrity, gender...to maintain the commitment and implementation of the Charter & Code criteria. | NEW-2024-2027
| Documents related to new principles elaborated and published (gender, open science, integrity, ...) | Q3 2025 | bar: 2025 Q2
| Action Plan updated incorporating any new principles that could be established | Q2 2024 | bar: 2024 Q2
A17 | Improve Researchers Assessment system in Recruitment | NEW- 2025
| A new system for new hirings for Researchers Assessment published | Q1 2025 | bar: 2025 Q1
| Number of Assessments done for Researchers Career Positions | Q4 2025 | bar: 2025 Q4; 2026 Q4; 2027 Q4
A18 | Design and implement the FSJD’s New Gender Plan. | NEW 2024-2029
| Define, prepare and implement the FSJD’s Gender Plan. | Q4 2024 | bar: 2024 Q4
| Outreach Activities done | Continuos | bar: 2024 Q1 to 2027 Q4
A19 | Infraestructures and Sustanaibility of Research | NEW-2024
| Infraestructure Policies defined and implemented | Q4 2024 | bar: 2024 Q4
| Plan for reducing carbon emissions elaborated | Q1 2025 | bar: 2025 Q1
A20 | Review and implement new talent policies (Desplegament del pla de Promoció de la Recerca IRSJD) | NEW-2024
| Career Evaluation Criteria and Process reviewed | Q4 2024 | bar: 2024 Q4
| New Calls for specific profiles opened | Q1 2025 | bar: 2025 Q1
| Stabilisation policy reviewed and published | Q3 2024 | bar: 2024 Q4